## Gantt Chart
Gantt Chart
TITLE: Virtual Reality Porject 5 Sniper Simulation | [6 empty] | University: |  |  |  |  | NDHU
PROJECT MANAGER: Zenroy Chance | [6 empty] | CREATION DATE: |  |  |  |  | 12/25
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
[7 empty] | DECEMBER | [21 empty] | JANUARY
[7 empty] | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | ST | S | M | T | W
1 | Design Plane | [5 empty] | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
1.1 | Creat Concept | Zenroy Chance | 12/27 | 12/27 | 1 | 100% | bar: DECEMBER T 27
1.2 | Paper Sketch | Zenroy Chance | 12/27 | 12/28 | 2 | 100% | bar: DECEMBER T 27 to DECEMBER W 28
1.3 | Gather assests needed | Zenroy Chance | 12/29 | 12/29 | 1 | 100% | bar: DECEMBER R 29
2 | Build Plane (Unity) |  |  |  |  | 100%
2.1 | Build compound | Zenroy Chance | 12/30 | 12/30 | 1 | 100% | bar: DECEMBER F 30
2.2 | Create weapon(s) | Zenroy Chance | 12/30 | 12/30 | 2 | 100% | bar: DECEMBER F 30
2.3 | Create Humanoids | Zenroy Chance | 12/31 | 4/31 | 1 | 100% | bar: JANUARY ST 31
3 | Code |  |  |  |  | 100%
3.1 | Write scripts (Movement, Ragdoll) | Zenroy Chance | 12/31 | 1/1 | 2 | 100% | bar: JANUARY ST 31 to JANUARY S 1
3.2 | Test & Improve | Zenroy Chance | 1/1 | 1/3 | 3 | 100% | bar: JANUARY S 1 to JANUARY T 3